## testing
Sr. No. | Bug No. | Bug decription | reported date | test procedure | Master or Slave | Modified HW/SW version | tester name | Testing location | resolution | resolved date | Dev. Name | Modified HW/SW version | tester's remark | Status
1 |  | we were unable to use variables from one .h file at different .c files |  |  | Slave |  | Priyanka | office | The solution for this problem which we found
| SW1 | it was giving duplication error. | 2022-02-15 |  | Master | V1.0.0 | Priyanka |  |  | 2022-02-21 | Prashant |  | Ok | Resolved
|  |  |  | Give +24v Power to J6 Connector 110v,19v,20vac to J26 connector ,connect remaining connector to slave PCB ,check on multimeter we get proper voltage on PCB or not then led gets turn ON indicating that PCB gets the power,check CAN communication led are blinking or not,check CAN,Vibrator,ADC,stepper motor work properly or not |  |  |  |  | #ifndef DELAY_VARIABLES_H_ // system generated #define DELAY_VARIABLES_H_ // system generated #ifndef DELAY_VAR // user defined # define _DELAY extern // user defined # define _DELAY_INIT(x) // user defined #else // user defined # define _DELAY // user defined # define _DELAY_INIT(x) = x // user defined #endif // user defined _DELAY _Bool msflag; // user defined _DELAY unsigned int mS_Cnt; // user defined _DELAY volatile _Bool ms100_flag; // user defined #endif /* DELAY_VARIABLES_H_ */ // system generated
2 | SW2 | Vibrator was operating for too much | 2022-02-15 |  |  | V1.0.0 | Priyanka | office | Added Math.h in main file and condition is written in code that if no. of cycles | 2022-02-21 | Prashant |  | OK | Resolved
|  | extra time and with extra cycles. | [6 empty] | is greater than defined or provided value then make it '0'.
|  | observation was the no of cycles were | [6 empty] | if(VBT_Cntr>VBRT_Cyl){
|  | increased for garbage value. | [6 empty] | VBT_Cntr = 0;}
3 | SW3 | while in run operation Weights of some | 2022-02-24 |  |  | V1.0.0 | Priyanka | office | Condition is added for this also that if settle time is greater than set value then | 2022-03-23 | Prashant |  | OK | Resolved
|  | heads were showing '0' and hence | [6 empty] | make it zero.
|  | recharge command was getting sent | [6 empty] | if(Settle_TMR > Settle_Time ){
|  | from master to that slave and it was | [6 empty] | Settle_TMR = 0;}
continiously doing the recharge resulting
weight bucket was getting full and
material was getting out from bucket.
4 | SW4 | Can communication is getting Off/not | 2022-03-07 |  |  | V1.0.1 | Priyanka | office | Still Working on it and below is the list of different trials taken so far. | 2022-03-23 | Prashant |  | OK | Resolved
responding after 20-21 minutes of
|  | operation. | [6 empty] | 1.tried chenging "timestamp_src" value and "timestamp_div" value
2.tried with low can speed it was 500kbps changed it to 34kpps
3.tried to reinitialize can when global error occurs.
4.tried avoiding checking can status
5.changed time stamp value to 1,2,4,8 initially it was 16(system generated)
6.changed receive mail boxex from 4 to 16
7.disabled error interrupts
8.changed value of global control register bit timestamp counter reset
9.tried commenting the clear messege ready instruction
10.tried changing RTBO value to 1 i.e. if bus is getting off then it will force fully
gets out of that mode.
11.Compared with old code and made the changes but still faced same issue.
12.when system was getting stopped then we were primaryly focusing on CAN
communication for that we were adding break point at receive isr of can but it was
not getting stuck there so because of that we were only focused on CAN.
but as we were stuck and tried with lots of possible option we decided go ahead
with code and for that we did put break point at run operation function code in
process can where we found out that after system stopped working it is observed
that can frames were getting received at that point.so problem was something
different.
→after that we monitored the run operation flags it is observed that when can
frame was received then its value was not getting changed to desired value.
so after further monitoring we came to know that the variable which is used
to decide slave id is getting some garbage value and the same variable is used to
extract data from can frame by left shiftting with slave id and hence as it was
extract data from can frame by left shiftting with slave id and hence as it was
→to get over this problem we written some logic to avoide garbage value in variable
but it didn’t work.
→so after that we decided to just switch on the system and do nothing and
monitored the variables which were getting garbage value but after running for 1 hour
it doesn’t affected the variables values.
→after that we decided to send only tare command which includes sending and
receiving of can frame i.e. full duplex communication it also worked fine for long time
(30 min) without affecting the variables values.(each command sent after every 1sec)
Unresolved
|  | After 20 min stepper motor stop |  |  | Slave |  |  | Office |  |  | Prashant |  |  | Unresolved | Testing inprogress
|  |  | 2022-03-22 |  |  | V1.0.2 | Priyanka |  | merg old/new stepper code |  |  | V1.0.3 |  |  | Resolved
|  | After 20 min stepper motor stop |  |  | Slave |  | Priyanka | Office | [5 empty] | Unresolved
|  |  | 2022-03-23 |  |  | V1.0.3 |  |  | Compare Old/new stepper Code |  | Prashant | v1.0.4
5 | SW5 | After 20 min stepper motor stop&Vibrator not working |  |  | Slave |  | Priyanka | Office | [5 empty] | Unresolved | Master
|  |  | 2022-03-24 |  |  | v1.0.4 |  |  | Commented the PMR.BYTE line in port.c file for portb and port 2 | 2022-03-28 | Prashant | v1.0.5 | OK | Resolved | Slave
|  | After 20 min stepper motor stop |  |  | Slave |  | Priyanka | Office
|  |  | 2022-03-25 |  | Slave | v1.0.5 |  | Office | All variables Initial values set to Zero or Non Zero. | 2022-03-31 | Prashant |  | OK | Resolved | Priyanka
Chaitanya
6 | HW1 | vreg pin of Tb6600 IC is not cut ,some components are missing on pcb & some components are of different value are solder on PCB | 2022-03-27 |  | Slave |  | Priyanka | Office |  | 2022-03-30 | Prashant |  | Ok | Resolved | Nana
7 | HW2 | Stepper Motor not rotate on new Slave PCB | 2022-04-04 |  | slave | v1.0.5 | Priyanka | Office | Use 22 pf capacitor across crystal because of clock issue,connect 104 Disc capacitor to Vreg pin (24) of TB6600 IC & give external 5v supply to stepper motor |  | Prashant |  |  | Unresolved | Dyaneshwar
8 | HW3 | Stepper Motor not rotate on new slave PCB | 2022-04-05 |  | slave | v1.0.5 | Priyanka | Office | Use 33 pf capacitor across crystal because of clock issue ,changes the crystal ,then check clk & enable signal is transmitted from controller to stepper motor correctly or not, that timing signal is transmitted from controller but it's not getting to motor |  | Prashant |  |  | Unresolved | Prashant
9 | HW4 |  | 2022-04-07 |  | slave | v1.0.5 | Priyanka | Office | Dry solder to transisitor of OPTO5 on slave PCB because of this dry solder ,clock was not getting to motor& then 47uf/63v capacitor is conncted to 24 pin of TB6600 IC | 2022-04-07 | Prashant |  | Ok | Resolved
10 | HW5 | No power isssue to 2 slave PCB ,Load Ptogram in 5 PCB but Adc & CAN Not working ,In 1 PCB program load ,CAN working but ADC not working,For 1 PCb load cell problem,For 1 PCB pin 2 of TB6600Ic is cut but in actual we need to cut pin 24 of TB6600 IC | 2022-04-08 |  | Slave | v1.0.5 | Priyanka | Office |  |  |  |  | NOT OK | Unresolved
11 | HW5 | ADC Problem | 2022-04-11 |  | Slave | v1.0.5 | Priyanka | Office | CAN Problem solved ,solder 8MHZ crystal to Y2 ,on PCB 4.9 MHZ crystal connected |  |  |  | NOT OK | Unresolved
For PCB1,2,5,7,10
For ADC, changes C13 ,C52,C74,C77 capacitor ,Inductor also ,changes C12,C6 capacitor in power supply section,C89,C25 Changres
On PCB Actual Required
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
R113 10k /1206 470ohm/1206
R141 470ohm/1206 10k/1206
12 | HW6 | ADC Problem | 2022-04-12 |  | Slave | v1.0.5 | Priyanka | Office | ADC problem of 1 new PCB solved ,Stepper Motor ,CAN ,vibrator is also check,stepper is remaining | 2022-04-12 | Prashant |  |  | Unresolved
Instead of L4,L5 Inductor ,in actual on PCB 102 /1206 capacitor is soldered
13 | HW6 | Hardware Testing Of New PCB | 2022-04-13 |  | Slave | v1.0.5 | Priyanka | Office | PCB 1,2,5,7,10 are OK . ADC,CAN Communication,StepperMotor,Vibrator all check ,Total 5 New Slave PCB are OK NOW | 2022-04-13 | Prashant |  | ok | resolved
In PCB 2 , change D9 Diode (SM24) of CAN Communication.
ON PCB Actual
D9 Diode BC857/SOT23 SM24
L1 102 /1206 100uH
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
PCB 3 -NOT Working
[9 empty] | PCB 4 - VCC & GND of R5F52315ADFL microcontroller IC is Short |  |  |  |  | Testing inprogress
ON PCB Actual
D9 Diode BC857/SOT23 SM24
L1 102 /1206 100uH
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
Testing inprogress
[9 empty] | PCB 6 - PCB Check but 330uH L1 inductor is heated |  |  |  |  | Testing inprogress
ON PCB Actual
D9 Diode BC857/SOT23 SM24
L1 102 /1206 100uH
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
[9 empty] | PCB 8 - No Power To ADC |  |  |  |  | Testing inprogress
ON PCB Actual
D9 Diode BC857/SOT23 SM24
L1 102 /1206 100uH
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
[9 empty] | PCB 9 - Not Working Properly |  |  |  |  | Testing inprogress
ON PCB Actual
D9 Diode BC857/SOT23 SM24
L1 102 /1206 100uH
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
14 | HW7 | Hardware Testing Of New PCB (14/04/22) | 2022-04-14 |  | Slave | V1.0.5 | Priyanka | Office | PCB 11 - TESTED OK (STEPPER1,STEPPER 2 ,VIBRATOR,CAN,ADC) | 2022-04-14 | Prashant |  | ok | Resolved
ON PCB Actual
D9 Diode BC857/SOT23 SM24
L1 102 /1206 100uH
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
[9 empty] | PCB 12- CAN Not Working, D9 Diode SM24 is changed,then CAN IC TJA1042 Soldered in wrong direction ,Stepper motor (FB & WB) working but it rotate Slowly , ADC Working |  | Prashant |  | Not Ok | Unresolved
ON PCB Actual
D9 Diode BC857/SOT23 SM24
R77 10K 2K2
L1 102 /1206 100uH
C13 104 /1206 22nf
C52 22nf 104/1206
C74 .C77 1uf 104/1206
C89 Black 102 102/1206
C25 Black 102 102/1206
CAN IC TJA1042 is soldered in wrong Direction
[9 empty] | PCB13 - At the starting 330 uH inductor Heated because of Vcc & GnD of R5f52315ADFL Microcontroller IC is short |  | Prashant |  | NOT OK | Testing inprogress
ON PCB Actual
C13 104 /1206 22nf
C52 22nf 104/1206
C74 ,C77 1uf 104/1206
C89 Black 102 102/1206
C25 Black 102 102/1206
R117 10 k 470ohm
R125 470 ohm 10k
R21 not soldered properly
Q17,Q112 not soldered properly
Instead Of R33 solder on R33 it is solder on C58
[9 empty] | PCB 14 - Program is loaded sucessfully but ADC ,CAN,Stepper not working |  | Prashant |  | NOT OK | Testing inprogress
ON PCB Actual
R19 4K7 1K
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C89 Black 102 102/1206
C25 Black 102 102/1206
Dry solder to Adc IC Pin
[9 empty] | PCB 15 - Program is loaded sucessfully but ADC ,CAN,FB not working,WB rotate |  | Prashant |  | NOT OK | Testing inprogress
CAN IC TJA1042 is soldered in wrong Direction
Q7.Q12,Q17 are dry solder
ON PCB Actual
R19 4K7 1K
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C89 Black 102 102/1206
C25 Black 102 102/1206
15 | HW8 | Hardware Testing Of new PCB | 2022-04-15 |  | Slave | V1.0.5 | Priyanka | Office | C74 1uf 104/1206 |  | Prashant |  |  | Testing inprogress
[9 empty] | PCB 13 - Tested Ok | 2022-04-15 |  |  | OK | Resolved
ON PCB Actual
R117 10 k 470ohm
R125 470 ohm 10k
C13 1uf/1206 22nf/1206
Q17,Q12 is not soldered Properly
Instead Of 4.7K soldered on R33 it is soldered on C58 capacitor - Feedbucket Section
R21 is not soldered Properly
Prashant
[9 empty] | PCB 14 - Tested Ok | 2022-04-15 |  |  | Ok | Resolved
ON PCB Actual
R19 470 ohm 1K
R117 10k 470 ohm
R125 470 ohm 10k
C51 22uf 104/1206
C95,C96 22uf 22pf
C25,C89 Black 102/1206 102/1206
Dry solder to pins of ADC IC CS5532
CRYSTAL OF 8MHZ CHANGES
[9 empty] | PCB 15 - Not Working |  |  |  |  | Testing inprogress
CAN IC TJA1042 is soldered in Wrong Direction
CAN not Working
[6 empty] | Total 8 PCB's are Working Properly right now |  |  | Adc Not Working
W,B is rotate
F.B is not rotate ,Q7,Q17,Q12 is not not soldered Properly
Stepper Ic TB6600 of FB Is Heated
D9 Diode BC857/SOT23 SM24
16 | HW9 | Hardware Testing Of new PCB | 2022-04-18 |  | Slave | V1.0.5 | Priyanka | Office | PCB 4 - No controller Power,VCC & GND of R5F52315ADFL microcontroller IC pins short problem is solved |  | Prashant |  |  | Testing inprogress
Check all pins of Microcontroller
ON PCB Actual
C12 100UH INDUCTOR 102 /1206 Capacitor
D9 Diode BC857/SOT23 SM24
C74 1uf 104/1206
C77 1uf 104/1206
[9 empty] | PCB 8 - Clock Issue of Microcontroller,No power To ADC problem is solved |  |  |  |  | Testing inprogress
ON PCB Actual
C89,C25 100uH inductor 102/1206
C94 10uf/35v TANT 1uf/35v
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C89 Black 102 102/1206
C25 Black 102 102/1206
C74 1uf 104/1206
C77 1uf 104/1206
[9 empty] | PCB 15 - Feed Bucket stepper Ic is Heated , CAN |  |  |  |  | Testing inprogress
ON PCB Actual
C94 10uf /35v TANT 1uf/35v TANT
R63 10K/1206 4K7/1206
R77 10K/1206 2K2/1206
D9 Diode BC857/SOT23 SM24
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C89 Black 102 102/1206
C25 Black 102 102/1206
C74 1uf 104/1206
C77 1uf 104/1206
CAN IC TJA1042 IS SOLDERED IN WRONG DIRECTION
[9 empty] | PCB 16 - CAN,ADC,STEPPER NOT WORK |  |  |  |  | Testing inprogress
ON PCB Actual
R63 10k 4K7
C94 10uf /35v TANT 1uf/35v TANT
R117 470ohm 10k
R125 470 0hm 10k
C95,C96 22uf 22pf
D9 Diode BC857/SOT23 SM24
R19 470ohm 1K
C13 104 /1206 22nf
Q17 -Dry Solder ,check Can IC TJA1042
Vcc & GND check .R121,R114 not assembled on PCB
[9 empty] | PCB 17 - Program not load |  |  |  |  | Testing inprogress
ON PCB Actual
R117 470ohm 10k
R125 470 0hm 10k
C95,C96 22uf 22pf
D9 Diode BC857/SOT23 SM24
C13 104 /1206 22nf
C52 22nf 104/1206
Vcc & GND check .
Pin 1 & 2 Of Microcontroller IC are Short
CAN IC TJA 1042 is soldered in opposite Direction
[9 empty] | PCB 18 - TESTED OK | 2022-04-18 | Prashant |  | ok | Testing inprogress
D29 is Changed
Put link in J10
Check waveform of Opto 6 & 5
ON PCB Actual
C95,C96 22uf 22pf
D9 Diode BC857/SOT23 SM24
Not OK
[9 empty] | PCB 19 - CAN not working |  |  |  |  | Testing inprogress
Vcc & GND check .
ON PCB Actual
C95,C96 22uf 22pf
R117 470ohm 10k
R125 470 0hm 10k
D9 Diode BC857/SOT23 SM24
TB6600 IC of stepper motor is not soldered
[9 empty] | PCB 20 - Clock Issue (microcontroller) |  | Prashant |  | Not Ok | Testing inprogress
ON PCB Actual
C95,C96 22uf 22pf
D9 Diode BC857/SOT23 SM24
8MHZ crystal is changed
22 PF Capacitor changes
Total 9 PCB's are Working Properly right now
17 | HW10 | Hardware Testing Of new PCB | 2022-04-19 |  | Slave | V1.0.5 | Priyanka | OFFICE | PCB 8 - Clock Issue of microcontroller solved ,ADC,CAN work |  | Prashant |  |  | Testing inprogress
Changes C95,C96 22pf caapcitor , 8MHZ crystal also changes ,D94 is soldered in wrong Direction.
NOW, ADC Problem Occurs
OPTO 9 solder in wrong direction
then ADC problem solved
Now,Stepper motor problem occurs
D21 diode connect in reverse direction
LD10 is not soldered properly ,
ON PCB Actual
R41 2k2 10k
still stepper motor problem is not solved
PCB 16 -program loaded sucessfully ,But Stepper motor,ADC ,CAN not work
SM24 D9 Diode changes,Q11 Dry solder
Done Touch Up to all trsnsisitor related to Feedbucket & Weightbucket
Microcontroller not reset so C47 104/1206 capacitor of reset button
PCB 19 - CAN work, stepper motor work
ADC not work , Calibration Done but sometime it shows ####
8MHZ crystal changes,Inductor of 100uH L4,L5 of ADC changes
TB6600IC is solderd
then stepper motor Feedbucket & weightbucket rotate
Testing inprogress
[9 empty] | PCB 20 - CAN WORK.W.B ,work ,ADC |  | Prashant
Clock Issue problem solved
8MHZ crystal of microcontroller changes
Q5 not solder properly
18 | HW11 | Hardware Testing Of new PCB | 2022-04-20 |  | Slave | V1.0.5 | Priyanka | OFFICE | PCB 4 - TESTED OK | 2022-04-20 | Prashant |  | OK | Resolved
No power to controller issue solved
D2 diode 1N5819 is missing on PCB
ON PCB Actual
R7 22k 10k
R41 2.2k 10k
8MHZ crystal changes
[9 empty] | PCB 8 - TESTED OK | 2022-04-20 | Prashant |  | OK | Resolved
stepper motor problem is solved
OPTO 5 OPTO 6 IN WB & FB SECTION IS SOLDERED IN OPPOSITE DIRECTION
[9 empty] | PCB 15 -TESTED OK | 2022-04-20 | Prashant |  | OK | Resolved
FEEDBUCKET IC Tb6600 is not heated now
OPTO 5 Of FB is soldered in wrong direction
ON PCB Actual
R41 2K2 10k
R46 104/1206 2K2
R42 104/1206 2K2
[9 empty] | PCB 20 -TESTED OK | 2022-04-20 | Prashant |  | OK | Resolved
F.B Problem solVED
R21 in feedbucket section Is not soldered properly
PCB 6 -TESTED OK
[10 empty] | 2022-04-20 | Prashant |  | OK | Resolved
ON PCB Actual
R7 10K 2K2
R63 10K 4K7
R41 2K2 10K
R19 4K7 1K
[9 empty] | PCB 12 -TESTED OK | 2022-04-20 | Prashant |  | OK | Resolved
4.9 MHZ crystal of ADC changes
Touch to Controller IC , ADC IC , Transistors related to CAN
Total 15 PCB's are Working Properly right now
[9 empty] | PCB 16 - Not working |  |  |  |  | Testing inprogress
ON PCB Actual
R41 2k2 10k
19 | HW11 | Hardware Testing Of new PCB | 2022-04-21 |  | Slave | V1.0.5 | Priyanka | OFFICE | PCB 19 - Tested OK | 2022-04-21 |  |  | Ok | Resolved
8 MHZ crystal changes
4.9 MHZ crystal changes
Opto 9 & 10 in ADC section changes
ADC IC Changes
Checked voltage across Transistor,resistor,Diode in ADC section
[9 empty] | PCB 16- Tested OK | 2022-04-21 |  |  | ok | Resolved
R110 changes
check voltage across each resisitor ,transistor,Diode related to ADC
Touch Up to controller IC
Total 17 PCB's are Working Properly right now

## Sheet1
PCB NO | Assembled | Require | BOM | REFERENCE PCB
PCB 1 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 caapcitor | 100uH | 100uH | 100uH
| L4 - 102 caapcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
PCB 2 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 caapcitor | 100uH | 100uH | 100uH
| L4 - 102 caapcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
PCB 3 | Y2 - 4.9152 MHZ Crysatl | 8 MHZ | 8 MHZ | 8 MHZ
PCB 4 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 caapcitor | 100uH | 100uH | 100uH
| L4 - 102 caapcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
PCB 5 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 caapcitor | 100uH | 100uH | 100uH
| L4 - 102 caapcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
PCB 6 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC847/sot23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 caapcitor | 100uH | 100uH | 100uH
| L4 - 102 caapcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
PCB 7 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 capcitor | 100uH | 100uH | 100uH
| L4 - 102 capcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
PCB 8 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 capcitor | 100uH | 100uH | 100uH
| L4 - 102 capcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
| C94 - 10uf/35v TANT | 1uf/35vTANT | 1uf/35vTANT
PCB 9 | Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ
PCB 10 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| R113 - 10k | 470ohm /1206 | 470ohm /1206 | 470ohm /1206
| R141 - 470ohm /1206 | 10k /1206 | 10k /1206 | 10k /1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 capcitor | 100uH | 100uH | 100uH
| L4 - 102 capcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| Y2 - 4.9152 MHZ Crystal | 8 MHZ | 8 MHZ | 8 MHZ
PCB 11 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 capcitor | 100uH | 100uH | 100uH
| L4 - 102 capcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
PCB 12 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 capcitor | 100uH | 100uH | 100uH
| L4 - 102 capcitor | 100uH | 100uH | 100uH
| C95 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf | 22pf/1206 | 22uf/1206 | 22pf/1206
CAN IC TJA1042 is soldered in wrong Direction
PCB 13 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| L5 - 102 capcitor | 100uH | 100uH | 100uH
| L4 - 102 capcitor | 100uH | 100uH | 100uH
| C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| R117 -10K/1206 | 470ohm/1206 | 470ohm/1206 | 470ohm/1206
| R125 - 470ohm | 10k/1206 | 10k/1206 | 10k/1206
R21 NOT SOLDERED PROPERLY
Q17,Q112 not soldered properly
Instead Of R33 solder on R33 it is solder on C58
PCB 14 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| R117 -10K/1206 | 470ohm/1206 | 470ohm/1206 | 470ohm/1206
| R125 - 470ohm | 10k/1206 | 10k/1206 | 10k/1206
| R19 - 470ohm | 1k/1206 | 1k/1206 | 1k/1206
Dry solder to pins of ADC IC CS5532
Crystal of 8MHZ changes
PCB 15 | C13- 104/1206 | 22nf /1206 | 22nf /1206 | 22nf /1206
| C52 - 22nf | 104/1206 | 104/1206 | 104/1206
| C74 - 1uf /1206 (105) | 104/1206 | 104/1206 | 104/1206
| C77 - 1uf /1206(105) | 104/1206 | 104/1206 | 104/1206
| C12 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C6 - - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C89 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| C25 - Black 102/1206 | White 102/1206 | White 102/1206 | White 102/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
CAN IC TJA1042 is soldered in Wrong Direction
Q7,Q17,Q12 is not not soldered Properly
PCB 16 | D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
| C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| R117 -10K/1206 | 470ohm/1206 | 470ohm/1206 | 470ohm/1206
| R125 - 470ohm | 10k/1206 | 10k/1206 | 10k/1206
| R19 - 470ohm | 1k/1206 | 1k/1206 | 1k/1206
Q17 -Dry Solder ,check Can IC TJA1042
.R121,R114 not assembled on PCB
PCB 17 | R117 -10K/1206 | 470ohm/1206 | 470ohm/1206 | 470ohm/1206
| R125 - 470ohm | 10k/1206 | 10k/1206 | 10k/1206
| C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
CAN IC TJA 1042 is soldered in opposite Direction
PCB 18 | C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22uf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22uf/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
D29 is Changed
Put link in J10
PCB 19 | R117 -10K/1206 | 470ohm/1206 | 470ohm/1206 | 470ohm/1206
| R125 - 470ohm | 10k/1206 | 10k/1206 | 10k/1206
| C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
PCB 20 | C95 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| C96 - 22uf/1206 | 22pf/1206 | 22uf/1206 | 22pf/1206
| D9 - BC857/SOT23 transistor | SM 24 -02 HTG | SM 24 -02 HTG | SM 24 -02 HTG
8MHZ crystal is changed
22 PF Capacitor changes

## Master
Sr. No. | Bug No. | Bug decription | reported date | test procedure | Modified HW/SW version | tester name | resolution | resolved date | dev. Name | Modified HW/SW version | tester's remark | Status

## Slave
Sr. No. | Bug No. | Bug decription | reported date | test procedure | Modified HW/SW version | tester name | resolution | resolved date | dev. Name | Modified HW/SW version | tester's remark | Status